## By Priority
# | Task | Original Type | Effort | Effort Hint | Impact | Breakdown / Sub-steps | Risks / Notes | Owner | Status
QUICK WIN (11) - Knock these out first - momentum + clear backlog fast
1 | Customer Inactive Option only for Admin | REQUIREMENT | XS | <= 2h | Med | Wrap toggle in role check (admin only) on UI + API guard. | None - simple role gate. |  | Pending
2 | user filter in target Report | CORRECTION | XS | <= 2h | Med | Add user dropdown filter; pass user_id to query. | Make sure default is 'All' for admins. |  | Pending
3 | user not allow to change there target | CORRECTION | XS | <= 2h | Med | Make target field read-only for non-admin role. | Confirm which roles can edit (admin/manager). |  | Pending
4 | Expiry Report Export option only Visiable with Admin | CORRECTION | XS | <= 2h | Low | Conditional render Export button based on role. | Same role-gate pattern. |  | Pending
5 | User Button Join with Profile | CORRECTION | XS | <= 2h | Low | Wrap user button in router-link to /profile/:id. | Confirm profile route exists. |  | Pending
6 | Lead report with last update detail | CORRECTION | XS | <= 2h | Med | Add 'Last Updated' column from existing updated_at field. | May need join if stored separately. |  | Pending
7 | Top Dashboard Header Fix | CORRECTION | XS | <= 2h | Low | CSS fix on dashboard header (alignment / sticky / overflow). | Verify across screen sizes. |  | Pending
8 | Customer Search Mobile Responsive | REQUIREMENT | S | 2-4h | High | Add responsive CSS breakpoints for search results table. | Test on actual mobile, not just resized browser. |  | Pending
9 | Tally API Update Button in Search | CORRECTION | S | 2-4h | Med | Add 'Update from Tally' button in search row; call existing tally hit endpoint. | Depends on Tally API task #1; may block. |  | Pending
10 | Our Serial Update Button Inactive | CORRECTION | XS | <= 2h | Low | Fix disabled state logic on Serial Update button. | Find why it's stuck disabled - likely a flag check. |  | Pending
11 | Create a seprate Option for Master IN this Add Item | CORRECTION | S | 2-4h | Med | Add 'Master' radio/toggle in Add Item form; route to master table. | Confirm UX with boss before building. |  | Pending
MEDIUM (11) - Standard feature work - half day to two days each
12 | Outstanding Report | REQUIREMENT | M | 0.5-2d | High | 1) DB query (party-wise outstanding) 2) API endpoint 3) UI table + filters 4) Export PDF/Excel | Define grouping: by party / by office / by aging bucket? |  | Pending
13 | Stock Summary Report Required | REQUIREMENT | M | 0.5-2d | High | 1) Aggregate stock by item/category 2) API 3) UI with filters (date, item) 4) Export | Confirm whether opening+closing or only current. |  | Pending
14 | New Party Ledger Report | REQUIREMENT | M | 0.5-2d | High | 1) Ledger query (debit/credit per party) 2) API 3) UI with date range 4) PDF export | Compare against existing party report - avoid duplicate. |  | Pending
15 | DashBoard Devide Sales and Outstanding, Customer | REQUIREMENT | M | 0.5-2d | High | Split dashboard into 3 cards/sections: Sales / Outstanding / Customers; add navigation drill-down. | Get layout mock from boss before coding. |  | Pending
16 | Category wise Amount and Quantity Define for Target | CORRECTION | M | 0.5-2d | Med | Extend target schema to per-category; UI to set qty + amount per category; rollup logic. | Migration if schema changes - check existing data. |  | Pending
17 | When Click expiry report then auto expiry update | CORRECTION | S | 2-4h | Med | On expiry-report load, trigger expiry status recompute (or scheduled job + manual trigger). | Heavy queries - run async if dataset large. |  | Pending
18 | Pending Report 2 option Required till Today Pending | CORRECTION | S | 2-4h | Med | Add 2nd pending option = pending up to today (vs current 'all pending'). | Clarify naming with boss to avoid confusion. |  | Pending
19 | External Task Report With Last Update Report | CORRECTION | M | 0.5-2d | Med | Add last_update column + filter to external task report; backend join with task_updates. | Index on updated_at for performance. |  | Pending
20 | Task Report Change Based on External Task | CORRECTION | M | 0.5-2d | Med | Modify task report to reflect external task linkage; UI + query change. | Define behavior when external task is deleted. |  | Pending
21 | Search Lastcall, Last Visit and Service Call popup | CORRECTION | M | 0.5-2d | Med | Popup component showing last call / last visit / service call history per customer in search. | Decide modal vs hover-card UX. |  | Pending
22 | Correction and requirement edit by the developer | REQUIREMENT | M | 0.5-2d | Med | Allow developer role to edit submitted correction/requirement entries (with audit trail). | Audit log mandatory - boss will want history. |  | Pending
BIG / WOW (5) - Major modules - need design + spec before coding
23 | Vouchers Tally API | REQUIREMENT | XL | 1-2 wk | High | 1) Auth with Tally 2) Voucher schema mapping 3) Push voucher endpoint 4) Pull voucher endpoint 5) Error/retry handling 6) Logging 7) Admin UI to monitor sync | Tally XML format quirks; offline queue if Tally is down. |  | Pending
24 | Tally api hit and Maintain Record for Updated Data | REQUIREMENT | XL | 1-2 wk | High | 1) Track updated_at per entity 2) Delta query API 3) Scheduled job (cron) to call Tally 4) Sync log table 5) Conflict resolution 6) Retry on failure 7) Dashboard for sync status | Idempotency critical - duplicate writes will corrupt Tally. |  | Pending
25 | Cloud Billing System | REQUIREMENT | XL | 1-2 wk | High | 1) Pricing/plan model 2) Subscription table 3) Invoice generator 4) Payment gateway integration 5) Customer billing UI 6) Admin reports 7) Webhooks for payment events | Major scope - get spec/wireframes before estimating dates. |  | Pending
26 | DataBase Auto Backup | REQUIREMENT | L | 3-5d | High | 1) mysqldump cron (daily + weekly) 2) S3/local rotated storage 3) Restore tested 4) Email/Slack alert on failure 5) Admin UI to download backup | Test RESTORE, not just backup. Untested backup = no backup. |  | Pending
27 | add Complain SEction | REQUIREMENT | L | 3-5d | High | 1) Complaint table + status enum 2) CRUD APIs 3) Customer-facing form 4) Admin queue UI 5) Assign-to-user 6) Status workflow 7) Email/SMS notifications | Define SLA/status flow with boss before schema. |  | Pending
INVESTIGATE (5) - Root-cause first; scope/effort unknown until reproduced
28 | Attendenace Report Error | CORRECTION | ? | TBD | Med | REPRO: which user/date triggers the error? Check logs, query, null fields. Likely fix: S-M. | Don't patch - find the actual bug; could indicate bad data. |  | Pending
29 | Billing Daybook Amount Error and Required Period | CORRECTION | ? | TBD | High | REPRO with sample dates. Check sum/aggregate query. Add period filter once amount issue is isolated. | Amount errors = customer-trust bug; reproduce with real numbers. |  | Pending
30 | Mobile no is Inactive but search Work 9706050760 | CORRECTION | ? | TBD | Med | Why is an inactive mobile returning in search? Check WHERE clause - missing is_active=1? | May be intentional for admin - confirm before fixing. |  | Pending
31 | Check out Lead Auto Buissness Closed | CORRECTION | ? | TBD | Med | Investigate auto-close logic for Lead/Business; what trigger fires it? Is rule correct? | Could be a cron or status-change trigger - audit both. |  | Pending
32 | Search Update issue | CORRECTION | ? | TBD | Med | Vague - get repro steps from boss/Vansh. What 'update' fails? In which screen? | Don't guess - clarify scope before estimating. |  | Pending

## Suggested Order
Day / Slot | Tier | Task | Effort | Why now
Day 1 AM | Quick Win | Top Dashboard Header Fix | XS | 5-min CSS - start with a guaranteed win
Day 1 AM | Quick Win | Our Serial Update Button Inactive | XS | Likely a flag check - quick fix
Day 1 AM | Quick Win | User Button Join with Profile | XS | Just a router-link - trivial
Day 1 PM | Quick Win | Customer Inactive Option only for Admin | XS | Single role-gate pattern - reuse it
Day 1 PM | Quick Win | Expiry Report Export option only Visiable with Admin | XS | Same pattern - cheap to ship together
Day 1 PM | Quick Win | user not allow to change there target | XS | Same role-gate pattern
Day 2 AM | Quick Win | user filter in target Report | XS | Add dropdown + query param
Day 2 AM | Quick Win | Lead report with last update detail | XS | Add column from existing field
Day 2 PM | Quick Win | Customer Search Mobile Responsive | S | Customer-facing - high impact
Day 2 PM | Quick Win | Create a seprate Option for Master IN this Add Item | S | Confirm UX first, then build
Day 3 AM | Investigate | Search Update issue | ? | Get clarity from boss/Vansh - blocks others
Day 3 AM | Investigate | Mobile no is Inactive but search Work 9706050760 | ? | Likely 1-line WHERE fix once reproduced
Day 3 PM | Investigate | Attendenace Report Error | ? | Reproduce + log dive
Day 4-5 | Medium | Outstanding Report | M | High impact - boss will see results
Day 4-5 | Medium | Stock Summary Report Required | M | Pair with Outstanding - similar plumbing
Day 6-7 | Medium | New Party Ledger Report | M | Third report - reuse export code
Day 8 | Medium | DashBoard Devide Sales and Outstanding, Customer | M | Visible to boss every login
Day 9 | Medium | Pending Report 2 option Required till Today Pending | S | Quick once context loaded
Day 9 | Medium | When Click expiry report then auto expiry update | S | Logic tweak
Day 10 | Medium | Search Lastcall, Last Visit and Service Call popup | M | Popup UX
Day 11 | Medium | External Task Report With Last Update Report | M | Pair with #22
Day 11 | Medium | Task Report Change Based on External Task | M | Same area as #21
Day 12 | Medium | Category wise Amount and Quantity Define for Target | M | Schema change - do mid-sprint
Day 13 | Medium | Correction and requirement edit by the developer | M | Audit-log heavy
Day 14 | Investigate | Billing Daybook Amount Error and Required Period | ? | Customer-money bug - debug carefully
Day 14 | Investigate | Check out Lead Auto Buissness Closed | ? | Audit auto-close trigger
Day 14 | Quick Win | Tally API Update Button in Search | S | Best done after Tally Big tasks have a working endpoint
Wk 3 | Big / Wow | DataBase Auto Backup | L | Lowest-spec Big - ship first to de-risk
Wk 3 | Big / Wow | add Complain SEction | L | Self-contained module
Wk 4-5 | Big / Wow | Vouchers Tally API | XL | Foundation for Tally sync
Wk 4-5 | Big / Wow | Tally api hit and Maintain Record for Updated Data | XL | Builds on Vouchers Tally API
Wk 6-7 | Big / Wow | Cloud Billing System | XL | Largest scope - needs spec from boss before starting

## Big-Wow Breakdown
Big Task | Sub-step # | Sub-step | Done?
Vouchers Tally API | 1 | Set up Tally connector lib + auth/handshake
| 2 | Map our Voucher schema -> Tally XML format
| 3 | Push voucher endpoint (POST /api/tally/voucher)
| 4 | Pull voucher endpoint (GET /api/tally/vouchers?since=...)
| 5 | Error handling + retry queue (failed pushes)
| 6 | Sync log table + admin UI to view status
| 7 | Test with real Tally instance (not mock)
Tally api hit and Maintain Record for Updated Data | 1 | Add updated_at column to all syncable entities (if missing)
| 2 | Build delta-query API (return rows updated since timestamp)
| 3 | Cron job: every N minutes, push deltas to Tally
| 4 | Sync_log table: entity, last_synced_at, status, error
| 5 | Idempotency: dedupe key so retries don't double-write
| 6 | Conflict resolution rules (latest-wins? manual?)
| 7 | Admin dashboard - sync health per entity
Cloud Billing System | 1 | Spec/wireframes from boss - DO THIS FIRST
| 2 | Plans + pricing tables (DB schema)
| 3 | Subscription model linking customer -> plan
| 4 | Invoice generator (monthly cron + on-demand)
| 5 | Payment gateway integration (Razorpay / Stripe / etc.)
| 6 | Customer billing UI (view invoices, pay)
| 7 | Admin reports - MRR, overdue, churn
| 8 | Webhooks for payment success/failure
DataBase Auto Backup | 1 | mysqldump script with daily + weekly rotation
| 2 | Storage location (S3 bucket OR external disk) + access keys
| 3 | Cron entry on server (verify it runs)
| 4 | Restore drill - prove the backup actually works
| 5 | Email/Slack alert on backup failure
| 6 | Admin UI to list + download backups
| 7 | Document the recovery procedure
add Complain SEction | 1 | Spec with boss - SLA, status flow, who-sees-what
| 2 | DB schema: complaints + complaint_updates + status enum
| 3 | CRUD API endpoints
| 4 | Customer-facing submission form
| 5 | Admin queue UI - filter by status / assignee
| 6 | Assign-to-user + reassignment workflow
| 7 | Status transitions (Open -> In Progress -> Resolved -> Closed)
| 8 | Email / SMS / WhatsApp notifications on status change

## Legend
Field | Values | Meaning
Tier | Quick Win | <=4h work, low risk - do first
| Medium | Half-day to 2-day standard feature work
| Big / Wow | Multi-day major module - needs spec first
| Investigate | Bug needs reproduction before scoping
Effort | XS | <= 2 hours
| S | 2 to 4 hours
| M | 0.5 to 2 days
| L | 3 to 5 days
| XL | 1 to 2 weeks
| ? | Cannot estimate yet (Investigate tier)
Impact | High | Customer-facing OR boss watches it OR money/data correctness
| Med | Internal team productivity / quality of life
| Low | Polish or rare-edge fix
Original Type | REQUIREMENT | New feature requested
| CORRECTION | Bug / fix to existing feature